## Status Report
Project Status Report
Customer |  |  | Mölnlycke Health Care |  |  | Status Report Date |  | 2022-12-20 | Over Project Status | Green
Customer Project Manager |  |  | Peter Wicander |  |  | Project Start Date |  | 2023-01-03
GTT Project Manager |  |  | Yana Dzhineva |  |  | Project Duration, weeks
GTT Project Code |  |  | PS-28956 |  |  | Project End Date |  | 2023-11-01
Project Milestone |  |  | Project Transition |  |  | Percentage of Project Completed |  | 35% | Risk Status | Amber
[9 empty] | Issue Status | Green
Project Dashboard
Current week
Order Created |  |  |  | 0
On Track |  |  |  | 37 |  |  |  |  | Open Issues | 0
Vendor Delivered |  |  |  | 11
CPE Installed |  |  |  | 0 |  |  |  |  | Open Actions | 0
Start of Service |  |  |  | 2
Fault Raised |  |  |  | 0 |  |  |  |  | Active Escalations | 0
Live Activated |  |  |  | 0
Delayed |  |  |  | 3
On Hold |  |  |  | 0
Cancelled |  |  |  | 1
| Disconnected |  |  | 0
Total Number |  |  |  | 54
Overall Status Summary
SD-WAN + uCPE Mölnlycke - Network Refresh PSQ-PM-220257 / PS-28956 Factories: High Availability in terms of uCPEs: Old uCPE + new uCPE. Regionals: We are keeping the current (old) uCPE + IPsec CPE There is one single new Factory site in Thailand where we are providing new uCPEs.
Main Issues / Risks
Regional sites CPE EOL
Key Deliverables This Period
Factory sites
Key Deliverables Next Period
n/a
Project Milestones
Milestone |  |  |  |  | Start Date |  | End Date |  | Status
Project Acceptance |  |  |  |  | 2022-12-16 |  | 2022-12-28 |  | Complete
Transition Review |  |  |  |  | 2023-01-03 |  |  |  | On Track
Service Handover
Project Closure
© GTT Communications, Inc. | [5 empty] | Private and Confidential

## Project Master Tracker
Project Master Tracker
CPON | GTT PON | Site type | Priority sites | Service type | Service bandwidth | Service ID: | Action required | Order Status | Latest update | MHC Actions | Next steps | CPE | IP info | Handoff | Vendor | Vendor FOC (circuit delivery date) | GTT FOC (final delivery date incl. equipment install. and LAN activation) | Verified shipping address | Site address | Post Code | Country | Site Contact | Site Contact Number | Site Contact Email | Site demarcations: Floor / Room / Cabinet Location
AE-DUB | 2214161 | Regional |  | SD-WAN | 110 Mbps-Dubai,AE | IR/mpls/01264396 | GTT | On Track | 01/05 Still pending design amendment 24/04 Pending order amendment with new design solution See below 03/04 Pending final solution 27/03 Escalaed 21/03 Clarity over the design solution is still pending 13/03 Pending analysis task 06/03 BEHIND NAT. USES GTT TRANSIT SUBNET SINCE ONLY 1 PUBLIC IP IS AVAILABLE ON CPA. THIS WILL NOT CHANGE UNLESS MHC CAN GET SOME MORE IPS. uCPE Silverpeak WAN0: 212.221.93.36/29 uCPE MGMT VM IP: 212.221.93.34 Gateway: 212.221.93.33 LAN: 10.244.136.254/28 Pending IP Assign - CPA x 2 (note: we have 2 x NEW CPA lines so do you want new IPs?) - reusing the same IPs from the existing CPA lines |  | Network Provision | existing CISCO1921-SEC/K9 plus uCPE COMPUTE 7200 4C-16R-500D-20Mbps + SP SD-WAN, WAN Opt, PA FW | uCPE Silverpeak WAN0: 212.221.93.36/29 uCPE MGMT VM IP: 212.221.93.34 Gateway: 212.221.93.33 LAN: 10.244.136.254/28 | Copper | CPA x 2 | n/a | n/a | ok | Units 603 and 604, Bldg Name: JBC1, Jumeirah Lake Towers, Dubai, -, United Arab Emirates | n/a | United Arab Emirates | Vinil Patteri | +971 58 9638 708 | vinil.patteri@molnlycke.com | Lvl 33; unit 3304
AT-VIE | 2234180 | Regional |  | SD-WAN | 110 Mbps-Wien,AT | GTT/002609280 | GTT | On Track | 01/05 Still pending design amendment 24/04 The cabling from the Colt handover to the end customer building is already ordered at KIM. As soon as I get an completion date I will inform you. 10/04 COLT to contract with KIM. GTT to contract with MHC. Pending vendor FOC and CISCO CPE TBC. 03/04 Costs to be explored to MHC 27/03 AM to discuss it with Peter on wednesday's meeting 20/03 Pending further details regarding the costs involved 13/03 Additional cabling is required (3rd party company is KIM) 06/03 Vendor can deliver on SMF; what kind of SFP will be required by MHC. 20/02 Pending FOC from Colt Technology Services and CPA IP details from MHC. |  | Fibre installation | uCPE 7200 and Cisco 1921-Sec/K9 | CPA AT-VIE uCPE Silverpeak WAN0: 80.64.141.13/29 uCPE MGMT VM IP: 80.64.141.11 Gateway: 80.64.141.9 | SMF | Colt Technology Services and CPA | TBC |  | ok | Wagenseilgasse 14 Wien 1120 Austria | 1120 | Austria | Christian Mueller | +436642417161 | christian.mueller@molnlycke.com | 2nd Floor, server room
AU-SYD | 2214230 | Regional |  | SD-WAN | 40 Mbps-Belrose,AU | GTT/002589489 | GTT | On Track | 01/05 Still pending design amendment 24/04 Pending order amendment with new design solution 10/04 Vendor deliveries are no track, however, still pending GTT final design solution. 03/04 Pending final solution 27/03 Cisco 1921-Sec/K9 TBC 21/03 to be clarified from which range we need PA space. If 16260 or 5580 is needed, then I’ll raise the task to IP Engineering team.) 20/03 Clarity over the solution design is still pending from SC, they advised that these might be put on hold 13/03 / 29 PA space. 06/03 Pending order validation and vendor FOC date 27/02 Pending installation of both fibre lines; reusing old equipment of GTT 20/02 Pending FOC (survey or/and install date) Order submitted; |  | Fibre installation | uCPE 7200 and Cisco 1921-Sec/K9 | TBC | Copper | AAPT & Pipe (TPG) and Vocus_acquired NexGen | TBC |  | ok | 12 Narabang Way, Belrose, 2085, Australia | 2085 | Australia | Karen Fox | +61438245184 | Karen.Fox@molnlycke.com | level 4, comms room, network rack
BE-ANT | 2214676 | Regional |  | SD-WAN | 110 Mbps-Antwerpen,BE | GTT/002589935) | GTT | Vendor Delivered | 01/05 Still pending design amendment 24/04 Service delivered, Pending PON amendment with new uCPE solution ASAP 10/04 See below 03/04 Pending vendor's delivery and GTT Cisco 1921-Sec/K9 TBC 27/03 See below 13/03 On track for April FOC DATE 07-Apr-2023 27/02 Pending FOC (survey date and fibre install) In progress |  | Fibre installation | uCPE 7200 and Cisco 1921-Sec/K9 | CPA BE-ANT uCPE Silverpeak WAN0: 94.107.200.133/29 uCPE MGMT VM IP: 94.107.200.134 Gateway: 94.107.200.129 | Copper | Colt Technology Services and CPA | TBC |  | ok | Berchemstadionstraat 72, Antwerpen, 2600, Belgium | 2600 | Belgium | Luc Dillen | '+32472902803 | luc.dillen@molnlycke.com | Level 2, server room
BE-WAR | 2234304 | Factory |  | SD-WAN | 600 Mbps-Waremme,BE | IR/mpls/01264249 | GTT | Vendor Delivered | 01/05 See below 24/04 Pending NNI change 10/04 Pending uCPE config and GTT provision 03/04 Pending final solution; TAD? 27/03 Pending design solution 21/03 the current uCPE 7200 is using a Proximus resell circuit for WAN0, NetProv doesn’t see this reflected in the CMD design, is this circuit going to be disconnected, is the old uCPE going to be connected to Proximus segment 12334528?) 20/03 Missing TAD/DCF 27/02 Still pending config. For uCPE 9400 20/02 Pending GTT uCPE Config Proximus renewal completed. Pending GTT uCPE config. And TAD |  | uCPE shipment | NEW uCPE 9400 + existing uCPE 7200 | TBC | Copper | Proximus x 2 | 2023-02-01 |  |  | Chaussée Romaine 176, Waremme, 4300, Belgium | 4300 | Belgium | Tomas Muller | +32496879958 | thomas.muller@molnlycke.com | ground floor, admin server room
BR-SAO | 2214655 | Regional |  | SD-WAN | 210 Mbps-Brooklin Paulista,BR | SD-WAN/01388034 | GTT | On Track | 01/05 Still pending design amendment 24/04 Pending vendor FOC and PON amendment with new design solution 10/04 See below 03/04 YD: Pending vendor SOF and GTT Cisco 1921-Sec/K9 TBC 27/03 Order submitted with the supplier 13/03 Pending ASR (order submission) 06/03 Missing TAD 27/02 ASR task escalated to VC management Pending order submission and CPE config + CPA IP info from MHC |  | Site Survey | NEW Cisco 1921-Sec/K9 + existing uCPE 7200 | uCPE Silverpeak WAN0: 179.191.76.155/29 uCPE MGMT VM IP: 179.191.76.154 Gateway: 179.191.76.153 LAN: 10.242.128.254/28 | TBC | ALGAR TELECOM + CPA | TBC |  |  | R. Castilho 392, 12th Room 122, Brooklin Paulista, 04568-010, Brazil | 04568-010 | Brazil | Rafael Machado | +55113016-8900 | rafael.machado@molnlycke.com | Level 12, rented office, server room
CA-OAK | 2214694 | Regional |  | SD-WAN | 20 Mbps-Oakville,CA | GTT/002589953 | GTT | On Track | 01/05 Still pending design amendment 24/04 Pending vendor FOC and PON amendment with new design solution 10/04 Clarity over the solution design is still pending from SC, they advised that these might be put on hold 03/04 Order placed with Bell, pending order processing. NOTE: CISCO1921-SEC/K9 TBC 27/03 Proceeding with option 2 20/03 We have 2 options here: 1. If MHC agree on Nadia/LCON approach/concern, then Peter needs to ask GTT to explore delivery options (different from Bell) then sales to be engaged. 2. if Peter prefers to go ahead with the solution signed, then he needs to coordinate it with the LCON (Nadia) and the project will go ahead in the way it was signed no further actions 13/03 Pending CPE config. GTT to check if vendor's HW replacement is part of this delivery 06/03 TAD to be updated: CA-OAK uCPE Silverpeak WAN0: 67.69.35.115/29 uCPE MGMT VM IP: 67.69.35.117 Gateway: 67.69.35.113 LAN: 10.242.184.254/28 |  | Site Survey | Existing uCPE 7200 and Cisco 1921-Sec/K9 | uCPE Silverpeak WAN0: 67.69.35.115/29 uCPE MGMT VM IP: 67.69.35.117 Gateway: 67.69.35.113 LAN: 10.242.184.254/28 | Copper | Bell Canada and CPA | TBC | TBC |  | 2010 Winston Park Dr, Oakville, ON, L6H 6P5, Canada | L6H 6P5 | Canada | Nadia Basile | +19058556012 | Nadia.Basile@molnlycke.com | 1st floor, suite 100 HUB server room (rented office)
CH-REG | 2214960 | Regional |  | SD-WAN | 210 Mbps-Schlieren,CH | GTT/002590219 | GTT | On Track | 01/05 Still pending design amendment 24/04 Pending vendor install and PON amendment with a new design solution 10/04 See below 03/04 Pending vendor's delivery and GTT Cisco 1921-Sec/K9 TBC 27/03 VENDOR FOC DATE: 5/4/23 13/03 NP notes: IP for GTT uCPE LAN0, Cisco CPE and VIP are needed, 10.244.240.241 is the current next hop in the LAN 06/03 Electrician contact is: Christian Peter christian.peter@habersaat-ag.ch Leiter Telecom / ICT, Mitglied der GL dipl. Techniker HF, Kommunikationstechnik Habersaat AG Bankplatz 4 8500 Frauenfeld M +41 79 537 07 68 D +41 52 725 03 04 Missing electrician contact |  | Fibre installation | Existing uCPE 7200 and Cisco 1921-Sec/K9 | uCPE Silverpeak WAN0: 81.62.190.226/29 uCPE MGMT VM IP: 81.62.190.228 Gateway: 81.62.190.225 LAN: 10.244.240.254/28 | Copper | Colt Technology Services and CPA | 2023-04-05 | TBC |  | Brandstrasse 24, Schlieren, 8952, Switzerland | 8952 | Switzerland | Barbara Böttcher and Electrician contact is: Christian Peter | +41798634888; M +41 79 537 07 68 D +41 52 725 03 04 | barbara.bottcher@molnlycke.com; christian.peter@habersaat-ag.ch | 11th floor, server room (badge required)
CN-BEI | 2217637 | Regional |  | MPLS | 20 Mbps-Beijing,CN | GTT/002592896 |  | Start of Service | 26/04 Service delivered and CPE installed by the vendor. 24/04 Pending vendor install and PON amendment with a new design solution 10/04 CPON will be helpful on this kind of list CN-BEI Backup: according to the Latest Notes: New vendor + CPE 03/04 Pending final solution 27/03 RS: Checking EoS of this model, 2911-SEK/K9 seems to be EoS like 1921 model. 21/03 This order has related MAC PON 1753140 (MHCG0/IPVPN/170106) ; CPE-MHCG0-IPVPN-170106 does not seem to be in production, both its LAN and WAN are not reachable and there are already 2 working CPEs at this site -> CPE-MHCG0-1816201-10180556 and CPE-MHCG0-IPVPN-217375 ; what exactly are we replacing here ? 20/03 Still pending design solution (escalated) 13/03 Pending CPE clarification 20/02 Vendor's lastmile provider is having network freeze between 1st-15th March 2023, resulting in limited operation during this period. This may cause a delay on circuit provisioning. CPE config |  | Completed | C921-4P | LAN 10.246.168.251/28 100.64.203.20/30 WAN | Copper | HGC Global Communications Limited | 2023-04-25 | 2023-04-26 |  | Mölnlycke Health Care Room 301, Building H Beijing Phoenix Plaza No.5A Shuguangxili Chaoyang District, Beijing, 100028, China | 100028 | China | Jim Jia | + 8613901022338 | China.IT@molnlycke.com | 3rd floor office space inside IT room on server rack (owned office)
| 2214987 |  |  | MPLS | 50 Mbps-Beijing,CN | GTT/002590246 |  | Start of Service | 26/04 Service delivered and CPE installed by the vendor. 24/04 Pending vendor install and PON amendment with a new design solution 10/04 Installation is scheduled for 17-Apr-2023. 03/04 Pending fibre delivery in April 27/03 X-connect completed. Pending fibre delivery. 13/03 Equinix x-conn to be ordered See below 27/02 Pending fibre install and x-connect 20/02 Pending vendor FOC and X-connect submission after the network freeze CPE config and check BMO |  | Completed | C921-4P | 10.246.168.251/28 LAN 100.64.203.16/30 WAN | Copper | HGC Global Communications Limited | 2023-04-17 | 2023-04-26 |  |  |  |  | Jim Jia | + 8613901022338 | China.IT@molnlycke.com | 3rd floor office space inside IT room on server rack
CZ-HAV | 2227128 | Factory |  | SD-WAN | 400 Mbps-Havirov,CZ | IR/mpls/01264838 | MHC | Vendor Delivered | 01/05 MHC suggested dates between May 9th to May 19th. Action plan to be confirmed. 24/04 uCPE pre-stage completed; uCPE delivered 6597551542 DHL; Next steps: -Installation of uCPE 9400 SN: CZJ3020N2H -LAN activation 10/04 Pending 3rd party supplier 03/04 Pending uCPE 9400 to be connected in ALEF WH for staging 27/03 RS: I confirm it as both circuits has the same performance so no matters where each circuit is connected to. 21/03 NP notes there is only 1 circuit working currently for CZ-HAV on a dedicated port on GTT's side, the cisco connected to it is to be removed and WAN0 on the old uCPE 7200 can be connected directly to it ; uCPE 9400 can be connected to segment 12309825 13/03 Pending uCPE config 06/03 Pending FOC 27/02 Vendor was asked to provide updates and advise if the delivery date is now confirmed. 20/02 Vendor received the information that the new feasibility was completed. Accordingly to the results (and matching end-customer´s modified requirements) the delivery will take about 5 weeks (around 22nd March). Once works start, vendor will provide more information. Next update will be requested on 22nd February. The estimated handover date is March 7th, however, an exact date will be available once vendor receives landlord´s permission and once the inhouse cabling is solved. | There are 2 options as per below. Please check and let me know which one suits you the best. 1) TTU install only – installation of NEW uCPE 9400 SN: CZJ3020N2H to the newly delivered line by CETIN (Line ID: 22981257) + upgrade of existing CETIN ID: 10290063 ~ 145806921 to 200Mbps – this can happen during business hours without any service disruption. 2) All in one (TTU plus LAN activation) – installation of equipment plus LAN activation making the conversion from Mpls to DIA and de-provisioning of old service/equipment that won’t be in use. Note that this will require downtime (around 15 mins) and out-of-hours activities. | uCPE install | NEW uCPE 9400 and existing uCPE 7200 | TBC | Copper | CETIN x 2 | 2023-03-07 |  |  | Dolni Sucha, Sachetni, Havirov, 73564, Czech Republic | 73564 | Czech Republic | Tomáš Borgoň | + 420727935178 | tomas.borgon@molnlycke.com | 1st floor, room 210 TBC
CZ-KAR | 2215005 | Factory |  | SD-WAN | 600 Mbps-Karviná,CZ | IR/mpls/01264931 | GTT | On Track | 01/05 Shipping request sent to Alef 24/04 Pending shipment of NEW uCPE 9400 SN: CZJ3020N2G 10/04 Vendor provided order form for cross-connect. Waiting for vendor to confirm if they will be ordering the X-connect or if GTT should do it. 03/04 Pending uCPE config 27/03 SOF sent to vendor. 13/03 Pending order submission 06/03 Site dmarks: 1st floor, server room. Site contact: Tomáš Borgoň Site phone: +420727935178 Site email: Tomas.Borgon@molnlycke.com 27/02 LCON contacted Missing site dmarks: room, rack, floor |  | Fibre installation | NEW uCPE 9400 and existing 7200 | TBC | Copper | CETIN x 2 | TBC | TBC |  | Na Novém poli 1, Karviná, 733 01, Czech Republic | 733 01 | Czech Republic | Roman Klimsza/Site contact: Tomáš Borgoň | + 420725986609; 420727935178 | roman.klimsza@molnlycke.com; Site email: Tomas.Borgon@molnlycke.com | TBC
CZ-PRA | 2234634 | Regional |  | SD-WAN | 40 Mbps-Praha 3,CZ | IR/mpls/01264968 | GTT | On Track | 01/05 Still pending design amendment 24/04 Pending order amendment with new design solution 10/04 YD: Pending GTT Provision Network - IP Port 03/04 Pending final solution 27/03 Analisys completed 20/03 Pending Analysis task 13/03 Pricing ID for the new Radio Link is 19611410. 06/03 Vendor update: Case ID 11359139 = VLAN 156 Fiber technology This is active service in our system with traffic on the line. Case ID 10500091 = VLAN 139 Radio technology. This is active service in our system but we also checked the service traffic and there is no traffic on this line. Please check with your customer if they are using this line. SPOF; Line ID 10500091 to be replaced with a NEW one |  | Fibre installation | Existing uCPE 7200 and CON-C1921-KT-X1 SN: FDO2206A2BL | TBC | Copper | CETIN x 2 | 2023-05-12 | TBC |  | Hájkova 22, Praha 3, 130 00, Czech Republic | 130 00 | Czech Republic | Eva Baresova | +420724306478 | eva.baresova@molnlycke.com | Level 2 omputer room
DK-ALL | 2215567 | Regional |  | SD-WAN | 110 Mbps-Lillerød,DK | IR/mpls/01264110 | Vendor | Delayed | 01/05 Still pending design amendment 24/04 Installation has been put on hold due to fire protection of all holes and fire escapes with audition. 12/04 EMERGENCY: TDC vendor update: Delivery has been put on hold, due to fire protection of all holes and fire escapes with audition. We can't really move forward until we have clarity on what exactly needs to be done. 10/04 TDC CPE installation is scheduled for 12/04/2023 and hand over will be sent by 19/04/2023.03/04. Pending fibre install FOC 19/04/2023. 13/03 TDC Access installation and CPE installation is scheduled for 12.04.2023; RFS is 19.04.2023 06/03 In progress; pending next delivery steps 27/02 Delivery is on track; The right address is Gydevang 39 20/02 LCON is not responsing as she wasn't aware of this delivery but now she is up to date. Vendor to try again. Vendor SOF agreement signed and sent over; pending FOC. |  | Fibre installation | existing uCPE 7200 + Cisco 881-SEK/K9 | TBC | Copper | GlobalConnect Sweden and TDC | 2023-04-19 |  |  | Gydevang 39, Lillerød, 3450, Denmark | 3450 | Denmark | Susanne Kopping | '+4548168254 | susanne.kopping@molnlycke.com | Level 1 server room
DK-HRS | 2234656 | Factory |  | SD-WAN | 100 Mbps-Horsens,DK | GTT/002609756) | Vendor | On Track | 01/05 Handover date remains 23rd of May. 24/04 Delivery is on track for May 10/04 Costs of 500EUR approved.The confirmed handover date remains 19th of May. 03/04 Pending MHC decision for the IHC. The first 50 meters are included in the price, but for the last 20 meters the price will be 500 EUR. 27/03 After the survey, the vendor found out that there will be a need for 70 meters in-house cabling in total. The first 50 meters are included in the delivery budget, but for the last 20 meters the price should be covered separately." Pending more details. 13/03 Service delivery is on track for April 06/03 uCPE delivered by DHL 4787687365. Estimated service delivery date remains 5th April. 27/02 Delivery address confirmed; DHL 4787687365; LCON is Kenneth Hüttel 20/02 Pending delivery address and consignee |  | Fibre installation | Existing uCPE 7200 plus NEW uCPE 5300 | TBC | Copper | TDC x 2 | 2023-05-23 | TBC |  | Vejlevej 3, M&J Airlaid AS, Horsens, 8700, Denmark | 8700 | Denmark | Kenneth Hüttel | +45 28 19 81 38 | kenneth.huttel@molnlycke.com | ground floor, servr room
EE-TAL | 2234191 | Regional |  | SD-WAN | 20 Mbps-Tallinn,EE | IR/mpls/01264413 | GTT | On Track | 01/05 Still pending design amendment 24/04 Pending vendor FOC and PON amendment with new design solution 10/04 Pending vendor FOC and final design solution to be confirmed for the market sites 03/04 Final setup & design for non-factory sites to be confirmed. 27/03 Order is in progress 13/03 Vabaõhumuuseumi tee 4/1 – 67 Tallinn Estonia 13/03 Pending address missmatch to be confirmed 06/03 Site address to be confirmed - email sent to Peter. "mising site info; address needs to be confirmed and aligned with the request to avoid confusion: PON address is "Vabaõhumuuseumi tee 4", quote address is: Vabaõhumuuseumitee 4/1. Offer is for Vabaõhumuuseumitee 4/2" |  | Order validation | existing uCPE 7200 and CISCO1921-SEC/K9 | uCPE Silverpeak WAN0: 84.50.180.117/29 uCPE MGMT VM IP: 84.50.180.115 Gateway: 84.50.180.113 LAN: 10.245.160.254/28 | Copper | Bite and CPA | TBC | TBC |  | TBC | TBC | Estonia | Ülle Siimaste | +3725145834 | ulle.siimaste@molnlycke.com | level 2 server room.
FI-HEL | 2215630 | Regional |  | SD-WAN | 20 Mbps-Helsinki,FI | GTT/001964633 | GTT | On Track | 01/05 Still pending design amendment 24/04 PON amendment with new design solution. Site address was confirmed. As per vendor request, the order form was amended and sent back to them. Vendor was asked to schedule the installation asap. 10/04 YD: Pending DNA install. Delivery date remains 10th of April. 03/04 Final setup & design for non-factory sites not yet clear 27/03 Delivery date remains 10th of April. 13/03 Ordering process started. Expecting order acceptance in the next 5 working days. 06/03 Order is in progress. Pending submission 27/02 LCON contacted Site dmarks to be confirmed - room, rack, floor plus LCON phone number |  | Order submission | existing uCPE 7200 and Cisco 1921-Sec/K9 | uCPE Silverpeak WAN0: 194.215.83.83/29 uCPE MGMT VM IP: 194.215.83.82 Gateway: 194.215.83.81 LAN: 10.244.216.254/28 | Copper | DNA and CPA | 2023-05-10 | TBC |  | Pitäjänmäentie 14, Helsinki, 00380, Finland | 380 | Finland | Oona Ahlstedt | TBC | oona.ahlstedt@molnlycke.com | TBC
FI-MIK | 2215653 | Factory |  | SD-WAN | 400 Mbps-Mikkeli,FI | IR/mpls/01377151 | Vendor | On Track | 01/05 Service delivery is On track for 26/05 24/04 Delivery is on track for May 10/04 Delivery date of the new Global connect line remains 26th of May. Confirmed date is yet to be provided. 03/04 Global Connect Lead time is 8 weeks - around 26th of May. Confirmed date is yet to be provided. 27/03 SOF sent to supplier 13/03 Order is in progress 06/03 Still pending site demarks 27/02 LCON contacted Site dmarks to be confirmed - room, rack, floor |  | Order validation | NEW uCPE 9400 and existing uCPE 7200 | TBC | Copper | GlobalConnect Sweden x 2 | 2023-05-26 | TBC |  | Saimaankatu 6, Mikkeli, 50100, Finland | 50100 | Finland | Jussi Huotari | +358406341452 | jussi.huotari@molnlycke.com | TBC
GB-MIL | 2227168 | Regional |  | SD-WAN | 130 Mbps-Milton Keynes,GB | GTT/002602251 | Vendor | Delayed | 01/05 BT order re-placed to the 2nd floor. Pending confirmation of TTB line. 24/04 Pending floor confirmation (case escalated) 10/04 One of the vendor's line is delivered. MHC to confirm the exact floor as there is a missmatch. Is it ground or 2nd floor? 03/04 Pending final solution 27/03 Pending X-conn segment TBC 20/03 Still pending design solution (escalated) 13/03 CPE TBC 06/03 Missing TAD 27/02 Order submitted 20/02 2nd LCON is Jay Turner +447790880202; jay.turner@molnlycke.com Missing secondary local contact | MHC to confirm the exact floor where the service should be delivered. | Site Survey | NEW uCPE 7200 | TBC | Copper | Talk Talk Business and British Telecom Wholesale | TTB 2023-03-28 | TBC |  | 401 Grafton Gate East, Molnlycke Health Care Ltd, Milton Keynes, MK9 1AT, United Kingdom | MK9 1AT | UK | Nigel Bubbear | + 447775703650 | nigel.bubbear@molnlycke.com | ground floor, comms room, comms rack
GB-OLD | 2215765 | Factory |  | SD-WAN | 200 Mbps-Oldham,GB | GTT/002591025 | MHC | Delayed | 01/05 Your order has hit a delay. Non specific TRC work requested by customer. SSRAMS required by customer. Please liaise with the customer and let us know if TRC is approved so we can progress with SSRAMs. Auto cancellation date - 17/05/2023. 24/04 Vendor chased to provide the TRCs, if they have not sent them to the client. **Pending uCPE Config and shipment 10/04 Pending TRC (time related charges) approval so vendor can progress with SSRAMs. 04/04 "Nonspecific TRC work requested by the customer. SSRAMS required by customer. Please liaise with the customer and let us know if TRC is approved so we can progress with SSRAMs." Pending more details from the supplier. 03/04 Survey performed on 30/03 (pending results); GTT UCPE config. in on track. 27/03 "Things are moving forward. Your order has now been accepted and achieved the status of Order Acknowledged (KCI1).Our supplier has confirmed that they have now completed initial planning checks for your order.We will review the progression of your order every 5 working days. Please note, more complex installations can take longer. We'll continue to keep you informed." 13/03 In progress 06/03 The installation point would need to be in the Main Comms Room, First Floor in Unity House. Rack 3. 27/02 LCON contacted Site dmarks to be confirmed - room, rack, floor 2nd LCON is Nigel Bubbear +447775703650 |  | Site Survey | NEW uCPE 7350 and existing uCPE 7200 | TBC | Copper | Talk Talk Business x 2 | TBC | TBC |  | Medlock Street, Molnlycke Healthcare, Oldham, OL1 3HS, United Kingdom | OL1 3HS | UK | Jay Turner or Nigel Bubbear | +447790880202 or ' +447775703650 | jay.turner@molnlycke.com or Nigel.Bubbear@molnlycke.com | TBC
HU-BUD | 2227349 | Regional |  | SD-WAN | 110 Mbps-Budapest,HU | IR/mpls/01264214 | GTT | Vendor Delivered | 01/05 Still pending design amendment 24/04 Pending order amendment with new uCPE solution 10/04 MHC: "If we only have a soft change, configuration change, this can be done any working day before or after the workday. Eg, Before 06.30 and after 18.00 CEST." 03/04 GTT Note: - the site currently has: 1xuCPE 7200 1xCISCO1921 (MPLS) - CPE-MHCG0-IPVPN-170016 1xCISCO1921 (IPSEC) - CPE-MHCG0-IPVPN-170082 - WAN1 (EMEA_MPLS) on the Dell is connected to the MPLS Cisco, if we deprovision the MPLS we'll break that connection 27/03 Pending De-Provision 20/03 Pending completion; Service renewal 13/03 HU-BUD uCPE Silverpeak WAN0: 89.134.149.132/29 uCPE MGMT VM IP: 89.134.149.130 Gateway: 89.134.149.134 LAN: 10.244.200.254/28 27/02 CPA info TBC 20/02 DTAG service renewed. Pending CPA IP information and site dmarks to be confirmed for admin purposes. | n/a | uCPE config | Existing uCPE 7200 | uCPE Silverpeak WAN0: 89.134.149.132/29 uCPE MGMT VM IP: 89.134.149.130 Gateway: 89.134.149.134 LAN: 10.244.200.254/28 | Copper | DTAG and NEW CPA | 2023-02-20 | TBC |  | Dévai u. 26-28, Budapest, 1134, Hungary | 1134 | Hungary | Zsolt Samarjai | +36309517564 | Zsolt.Samarjai@molnlycke.com | TBC
IT-GAL | 2216011 | Regional |  | SD-WAN | 20 Mbps-Gallarate,IT | GTT/002591270 | GTT | On Track | 01/05 Still pending design amendment 24/04 Site contact is not responsing (email sent) 10/04 Pending SOF for more than 5 business days. Automatic escalation has been triggered. 03/04 Final setup & design for non-factory sites not yet clear 27/03 Order submitted; pending next delivery stage 20/03 АSR escalated 13/03 Pending ASR 06/03 Order is in progress, pending submission 27/02 LCON contacted Missing site demarks |  | Order submission | CISCO1921-SEC/K9 and uCPE 7200 | uCPE Silverpeak WAN0: 151.0.141.134/28 uCPE MGMT VM IP: 151.0.141.133 Gateway: 151.0.141.129 LAN: 10.244.169.254/28 | Copper | FASTWEB and CPA | TBC | TBC |  | Via Marsala 40c, Gallarate, 21013, Italy | 21013 | Italy | Laura Molteni | +39 0331 714011 | Laura.Molteni@molnlycke.com | TBC
JP-TOK | 2227182 | Regional |  | SD-WAN | 110 Mbps-Tokyo,JP | GTT/002602265 | GTT | On Track | 01/05 Still pending design amendment 01/05 Site visit to be arranged with Cordeos + Hanafi Noor (Hanafi.Noor@molnlycke.com) in Copy. 10/04 Pending alternative LCON as the current one is not aware of this delivery based on the vendor's report. 03/04 Final setup & design for non-factory sites not yet clear 27/03 Pending next appointment 20/03 Building name confirmed by MHC, however, LCON is to be confirmed; MHC: ".. In Japan we do not have IT person here. All IT works are in charge of the company called Cordeos.Twice a week, they will visit our site and support either directly or through our website." 13/03 JP-TOK CPA info to be confirmed GATEWAY IS CURRENTLY GTT IPSEC CPE, WHICH IS IN PATH. NEEDS CHECKING WITH PETER WHAT NEW ALLOCATION WILL LOOK LIKE. uCPE Silverpeak WAN0: 150.249.225.76/29 uCPE MGMT VM IP: 150.249.225.74 Gateway: 150.249.225.73 LAN: 10.246.160.254/28 06/03 Pending LCON to confirm building name, site address and dmarks 27/02 LCON is not aware. RFS and Building name TBC 20/02 New access line with Colt which will re-place current access line with Telstra. CPA will be re-placed by CPA-Enhanced. uCPE 7200, Alef CPE Cisco 1921-Sec/K9, IPSec and PA-VM were moved from the existing order. Order confirmed | redesign CPA line | Order submission | Existing uCPE 7200 and Cisco 1921-Sec/K9 | GATEWAY IS CURRENTLY GTT IPSEC CPE, WHICH IS IN PATH. NEEDS CHECKING WITH PETER WHAT NEW ALLOCATION WILL LOOK LIKE. uCPE Silverpeak WAN0: 150.249.225.76/29 uCPE MGMT VM IP: 150.249.225.74 Gateway: 150.249.225.73 LAN: 10.246.160.254/28 | Copper | COLT Asia and CPA | TBC | TBC |  | 6-chōme-20-7 Nishishinjuku,Shinjuku City, Tokyo, 160-0023, Japan | 160-0023 | Japan | Megumi Toyama | +81 36914 5004 | Megumi.Toyama@molnlycke.com | Level 4 owned office, server room
KR-SEO | 2216029 | Regional |  | SD-WAN | 30 Mbps-Songpa-gu, Seoul,KR | IR/mpls/01264404 | GTT | On Track | 01/05 Still pending design amendment 24/04 There is a slight increase of the MRC after the survey, pending approval 10/04 Pending new appointment 03/04 YD: Site survey has returned and there is only one provider who can service the buiding. With this in mind there is a small increase in price – Install - $ 0 USD MRC - $ 935 USD 27/03 Order submitted but price has been changed 20/03 Pending ASR (order submission) GTT is on it 20/02 Missing TAD and check CPA IPs |  | Order validation | Existing uCPE 7200 and CISCO1921-SEC/K9 | uCPE Silverpeak WAN0: 59.9.164.202/28 uCPE MGMT VM IP: 59.9.164.201 Gateway: 59.9.164.206 LAN: 10.246.176.254/28 | Copper | Gateway and CPA Global_PCCW_HKT and CPA | TBC | TBC |  | 28, Beobwon-ro 11-gil, BK Tower 6th floor, Songpa-gu, Seoul, 05836, South Korea | 5836 | South Korea | Jee Ae Park | +82 102208 8302 | JeeAe.Park@molnlycke.com | Level 6, owned office, comms rack
LT-VIL | 2216046 | Regional |  | SD-WAN | 20 Mbps-Vilnius,LT | IR/mpls/01264421 | GTT | Vendor Delivered | 01/05 Still pending design amendment 24/04 Pending order amendment with new uCPE solution 10/04 MHC: "If we only have a soft change, configuration change, this can be done any working day before or after the workday. Eg, Before 06.30 and after 18.00 CEST."03/04 GTT Note: - The site currently has: 1xuCPE 7200 1xCISCO1921 (IPSEC) as secondary - CPE-MHCG0-IPVPN-170102 1xCISCO1921 (IPSEC) as tertiary - CPE-MHCG0-IPVPN-170112 No MPLS circuit here 27/03 Pending deprovision of old solution 20/03 GTT is on it; CPA requirements TBC 13/03 To be confirmed 06/03 NO IPS AVAILABLE FOR SILVERPEAK, SO IT IS USING PRIVATE GTT TRANSIT SUBNET. UNLESS PETER CAN GET SOME MORE IPS AT THIS SITE, THIS WILL NOT CHANGE. uCPE Silverpeak WAN0: 192.168.255.2/29 uCPE MGMT VM IP: 88.119.204.161/24 Gateway: 88.119.204.1 (192.168.255.1 for Silverpeak) LAN: 10.245.152.254/28 Pending IP Assign CPA x 2 | n/a | uCPE config | CISCO1921-SEC/K9 and uCPE 7200 | NO IPS AVAILABLE FOR SILVERPEAK, SO IT IS USING PRIVATE GTT TRANSIT SUBNET. UNLESS PETER CAN GET SOME MORE IPS AT THIS SITE, THIS WILL NOT CHANGE. uCPE Silverpeak WAN0: 192.168.255.2/29 uCPE MGMT VM IP: 88.119.204.161/24 Gateway: 88.119.204.1 (192.168.255.1 for Silverpeak) LAN: 10.245.152.254/28 | n/a | CPA x 2 | n/a | n/a |  | J. Galvydžio g. 5, Vilnius, 08236, Lithuania | 8236 | Lithuania | TBC | TBC | TBC | not required
MY-BK | 2216168 | Factory |  | SD-WAN | 80 Mbps-Batang Kali,MY | GTT/002459195 | GTT | Vendor Delivered | 01/05 MY-BK 2216168 - date suggested 9th May at 3 pm local time 24/04 MHC to provide install date asap 10/04 See below 03/04 Pending installation of GTT uCPE 5300 SN: 95267C3 27/03 Final POD provided. Equipment is delivered. 20/03 Escalated for more details 13/03 Pending tracking link 06/03 Pending uCPE delivery uCPE shipment is in progress |  | uCPE install | NEW uCPE 5300 + existng uCPE 9300 | TBC | Copper | IX Telecom and SG.GS | delivered | 2022-08-08 and 2022-07-29 |  | Mölnlycke Health Care Sdn. Bhd., Lot No. B5 & B6, Kawasan Perindustrian MIEL, Batang Kali Phase II, Batang Kali, 44300, Malaysia | 44300 | Malaysia | Kwang San | +604-4891819 EXT: 450 | kwangsan.ang@molnlycke.com | Lvl 2, Factory building, comms room
MY-KH | 2216188 | Factory |  | SD-WAN | 100 Mbps-Kulim,MY | GTT/002459197 | GTT | Vendor Delivered | 01/05 MY-KH 2216188 -date suggested 10th May at 3 pm local time 24/04 MHC to provide install date asap 10/04 See below 03/04 Pending install of GTT uCPE 5300 SN: D5R57C3 27/03 Final POD provided. Equipment is delivered. 20/03 Escalated for more details 13/03 Pending tracking link 06/03 Pending uCPE delivery uCPE shipment is in progress |  | uCPE delivery | NEW uCPE 5300 + exisitng uCPE 9300 | TBC | Copper | Telekom Malaysia Bhd_TM x 2 | delivered | 16.8.2022 and 2022-08-08 |  | Mölnlycke Health Care Sdn. Bhd Jalan Hi-tech 7, Kulim Hi-tech Park, Kulim, 09000, Malaysia | 9000 | Malaysia | Kwang San | +604-4891819 EXT: 450 | kwangsan.ang@molnlycke.com | Lvl 1, MDF 1.1, Factory building,
MY-KK | 2216194 | Factory |  | SD-WAN | 80 Mbps-Kuala Ketil,MY | GTT/002459196 | GTT | Vendor Delivered | 01/05 MY-KK 2216194 - date suggested 11th May at 3 pm local time 24/04 MHC to provide install date asap 03/04 Pending install of GTT uCPE 5300 SN: 8ZY67C3 27/03 Final POD provided. Equipment is delivered. 20/03 Escalated for more details 13/03 Pending tracking link 06/03 Pendingg uCPE delivery uCPE shipment is in progress |  | uCPE delivery | Existing uCPE 9300 + NEW uCPE 5300 | TBC | Copper | Cypress Telecom Ltd and IX Telecom | delivered | 5.8.2022 and 2022-08-02 |  | Mölnlycke Health Care Sdn. Bhd., Plot 204, Kawasan Perindustrian Kuala Ketil,, Kuala Ketil, 09300, Malaysia | 9300 | Malaysia | Kwang San Ang | +604-4891819 EXT: 450 | kwangsan.ang@molnlycke.com | Level 2, factory building, server room
MY-KUA | 2216202 | Regional |  | SD-WAN | 50 Mbps-Shah Alam,MY | IR/dia/01314965 | GTT | On Track | 01/05 Still pending design amendment 24/04 Pending Vendor Construction and GTT PON amendment with new design solution 10/04 Vendor update: We scheduled the fiber cable installation on 31st March 2023 due to earlier rescheduling from end customer and currently awaiting approval work permit approval from building management . Will keep you posted once the fiber cable installation work commerce and lead time work progress. 03/04 Final setup & design for non-factory sites not yet clear 31/03 UCPE SN: CRPJ8K3 (shipped) 20/03 Pending vendor FOC 13/03 IP Assign - PA Space 6268817 06/03 TAD will be uploaded in 2 days GTT is on it 20/02 Pending TAD Order confirmed |  | Order submission | existing uCPE 7200 +CIS-1921-SEC/K9 | uCPE Silverpeak WAN0: 121.123.174.101/29 uCPE MGMT VM IP: 121.123.174.99 Gateway: 121.123.174.97 LAN: 10.246.144.254/28 | Copper | TIME_ fka Global Transit Communications and CPA | TBC | TBC |  | Selangor Darul Ehsan Lot 7-3 Level Upper Ground UOA Business Park No.1 Jalan Pengaturcara U1/51A Seksyen U1, Shah Alam, 40150, Malaysia | 40150 | Malaysia | Amir Saifuddin | + 60137317311 | Amir.Saifiuddin@molnlycke.com | Level 2 server room, owned office
MY-KUL | 2227027 | Factory |  | SD-WAN | 200 Mbps-Kulim,MY | GTT/002459194 | Vendor | On Track | 01/05 Pending install. date 24/04 Requested vendor to share install date; Pending FOC. 11/04 uCPE shipped; SCM: Pending FedEx pickup: 3970 9635 7299. For further updates please see TecEx tracking link: https://www.tecex.com/tracking?q=365426MY 10/04 Pending vendor FOC 03/04 Requested vendor to share current status of the order and also to get us the FOC date ASAP. 22/03 Pending uCPE config 20/03 Site survey booked on 21st Mar (Tuesday) @2:00PM. 13/03 SCM task to be raised once the confg of uCPE 7350 is done 09/03 Telekom upgrade to 100 completed, pending new delivery 20/02 Pending uCPE Config (Exotic) |  | Site Survey | Existing uCPE 7200 plus NEW uCPE 7350 | LAN subnet: 10.245.105.251/28 | Copper | Telekom Malaysia Bhd_TM x 2 | TBC | TBC |  | Lorong Perusahaan 4, Kulim, 09000, Malaysia | 9000 | Malaysia | Kwang San Ang | +604-4891819 EXT: 450 | kwangsan.ang@molnlycke.com | Level 1, factory building, server room
NL-UTR | 2216218 | Regional |  | SD-WAN | 50 Mbps-Utrecht,NL | GTT/001845085 | GTT | On Track | 01/05 Still pending design amendment 24/04 Pending order amendment with new design solution. Order is on track for May. The client confirmed that T-Mobile should use 30251-AN03-002/00-0 for the delivery. As a result, the order was processed and received FOC date of 2-MAY-2023. On 19/04 T-Mobile performed SFP installation, however it was not successful due to unclarity on vendor's end. T-Mobile are working on re-scheduling, next update is expected on 25th April. 10/04 YD: Delivery is in progress; MHC advised to use 30251-AN03-002/00-0 (T-Mobile device). However, GTT is still working on the final design solution for the regional sites. 03/04 No response yet 27/03 Still pending MHC's LCON to check vendor's devices if they can be used for the current order 20/03 During the feasibility check, T-Mobile found out that they can deliver on multiple existing devices. The vendor needs to know if one of the below can be used: ***snip*** 30251-AN03-001/00-0 30251-AN03-002/00-0 30251-AN03-004/00-0 30251-AN03-005/00-0 13/03 VC has placed the order with T-Mobile via the vendor's online spot portal. Pending the vendor to confirm that the feasibility check has begun. 06/03 Order is in progress 27/02 LCON contacted Still missing site dmarks |  | Site Survey | CON-C931P4-2KT-X1 and uCPE 5300 | uCPE Silverpeak WAN0: 82.201.93.20/29 uCPE MGMT VM IP: 82.201.93.19 Gateway: 82.201.93.17 LAN: 10.245.168.254/28 | Copper | T-Mobile and CPA | 2023-05-02 | TBC |  | Van Deventerlaan 31-51, Office Number 3.01 (B-side), Utrecht, 3528 AG, Netherlands | 3528 | Netherlands | Luc Dillen | +3232868968 | luc.dillen@molnlycke.com | TBC
NO-OSL | 2227220 | Regional |  | SD-WAN | 70 Mbps-Oslo,NO | GTT/002602303 | GTT | On Track | 01/05 Still pending design amendment 24/04 Vendor delay: Escalation was raised to the vendor to confirm the completion of the delivery and provide handover. Separately, pending GTT PON amendment with new design solution. 10/04 Delivery date remains 14th April. 03/04 Final setup & design for non-factory sites not yet clear 20/02 Pending vendor FOC and CPE TBC |  | Site Survey | uCPE 7200 and Cisco 1921-Sec/K9 | uCPE Silverpeak WAN0: 213.52.70.101/29 uCPE MGMT VM IP: 213.52.70.99 Gateway: 213.52.70.97 LAN: 10.245.80.254/28 | Copper | GlobalConnect Norway and CPA | 2023-04-14 |  |  | Brynsalléen 4, Oslo, 0667, Norway | 667 | Norway | Lisa Andersen | +4797019013 | lisa.andersen@molnlycke.com | 5th floor, server room
PL-WAW | 2216902 | Regional |  | SD-WAN | 20 Mbps-Warszawa,PL | GTT/002592161 |  | Cancelled | [10 empty] | Okopowa 58, Warszawa, 00, Poland
DE-DUS | 2366591 | Regional |  | SD-WAN | 100 Mbps-Düsseldorf,DE | (GTT/002598444) | GTT | On Track | 01/05 Still pending design amendment 24/04 Delivery is on track for May. Meanwhile, pending order amendment with new design solution 10/04 Pending DTAG fibre install (on track for May) 03/04 Pending the fibre delivery |  | Fibre installation | Existing CON-C892FSP-KT SN: FCZ202491BW + Existing CIS-ISR4331-SEC/K9 plus uCPE 7200 | TBC | Copper | COLT and DTAG | COLT service delivered on , pending DTAG line in May | TBC |  | Grafenberger Allee 297 Düsseldorf 40237 Germany | 40237 | Germany | Stephan Habenicht | +4921192088108 | stephan.habenicht@molnlycke.com | 8th floor, server room
SA-JED | 2216929 | Regional |  | SD-WAN | 40 Mbps-Jeddah,SA | SD-WAN/01595202 | GTT | On Track | 01/05 Still pending design amendment 24/04 Pending order amendment with new design solution. See below 03/04 Pending final solution 21/03 То be clarified, see below: 06/03 there are 2*CPA in the order signed. Pending IP Assign - CPA x 2 - only 1 CPA line? TBC; Cisco CPE TBC if new or existing? |  | Network Provision | uCPE 7200 (existing) and new Cisco 1921-Sec/K9 | uCPE Silverpeak WAN0: 37.224.121.35/29 uCPE MGMT VM IP: 37.224.121.34 Gateway: 37.224.121.33 LAN: 10.244.152.254/28 | Copper | CPA x 2 |  |  |  | Prince Mohammed Bin Abdulaziz St, Prince Mohammed Bin Abdulaziz St, Al Andalus, Jeddah, 23326, Saudi Arabia | 23326 | Saudi Arabia | Agsan Alosimi | +966555061106 | agsan.alosimi@molnlycke.com | Level 2 server room
SE-GOT | 2216937 | Regional |  | SD-WAN | 1200 Mbps-Gamlestaden,SE | IR/mpls/01265154 | GTT | Vendor Delivered | 01/05 Still pending design amendment 24/04 Pending order amendment with new uCPE solution 10/04 MHC: "If we only have a soft change, configuration change, this can be done any working day before or after the workday. Eg, Before 06.30 and after 18.00 CEST." 03/04 GTT Note: - the site currently has: 1xuCPE 7200 1xCisco 892 (MPLS) - CPE-MHCG0-IPVPN-471106 1xISR4331 (IPSEC) - CPE-MHCG0-IPVPN-420739 - i see no C2911 being used or to have been used for that site - if we deprovision the MPLS, we will break the WAN1 circuit 27/03 Pending De-Provision 20/03 Pending completion 13/03 Pending test |  | uCPE config | existing uCPE 7200 + NEW Cisco 2911-SEK/K9 | uCPE Silverpeak WAN0: 212.247.47.38/27 uCPE MGMT VM IP: 212.247.47.35 Gateway: 212.247.47.62 LAN: 10.245.15.254/28 | Copper | GlobalConnect Sweden (IP only) and CPA | delivered |  |  | Gamlestadsvägen 3C, Gamlestaden, 415 02, Sweden | 415 02 | Sweden | Henrik Bernwald | + 46313523836 | henrik.bernwald@molnlycke.com | server room, floor 2
SG-SIN | 2216940 | Regional |  | SD-WAN | 80 Mbps-Singapore,SG | GTT/002592199 | GTT | On Track | 01/05 Still pending design amendment 24/04 Pending order amendment with new design solution 10/04 Pending config. and shipment of C921P4-IPSEC. Also, pending vendor FOC. 03/04 Pending CISCO delivery 27/03 SC feedback: "it’s the site where the 1921 has been replaced by a new 921 one… so I confirm that the EPT ID is correct - C921P4-IPSEC." 20/03 Still pending design solution (escalated) 13/03 Still pending CPE clarification 27/02 CISCO CPE TBC (GTT) 21/02 Current CPE belongs to the old vendor (Telstra) that will be ceased. New solution: New GTT CPE is needed from Alef. As we are NOT going to keep the current vendor circuit, we are not going to keep the CPE as well so a new one (same model) is needed. 20/02 CPE to be clarified Order confirmed. Pending vendor FOC |  | Fibre installation | existing uCPE 7200 and NEW Cisco 1921-Sec/K9 | uCPE Silverpeak WAN0: 115.42.196.133/28 uCPE MGMT VM IP: 115.42.196.130 Gateway: 115.42.196.129 LAN: 10.246.128.254/28 | Copper | ViewQwest_VQ and CPA | TBC |  |  | 298 Tiong Bahru Rd, #07-03/04/05/06, Singapore, 168730, Singapore | 168730 | Singapore | Hanafi Noor | +65 6501 4149 | hanafi.noor@molnlycke.com | Level 7, Owned office, server room
TH-BAN | 2216956 | Factory |  | SD-WAN | 200 Mbps-Samutprakarn,TH | GTT/002592215 | Vendor | On Track | 01/05 Telstra delivery escalated 24/04 HGC circuit is delivered; pending Telstra 11/03 uCPE delivered 10/04 B End : Mullige Health Care (Thailand) Company Limited HQ Mr. Yutthana 083-0970203 • Site Survey - Completed on 20/03/2023 • Training - Pending on 20-21/04/2023 09:00AM onwards Around 2hr. before work. • Installation fiber optic - Pending on 20-21/04/2023 09:00AM onwards As plan the end customer • Installation Equipment + TestSpeed - TBC 03/04 YD: NEW uCPE 7350 SN: CRPJ8K3 (delivered). Pending fibre deliveries. 27/03 Pending survey status and tracking info for the equipment sent to client's site 22/03 uCPE shipped 21/03 Missing TAD 13/03 PendingTAD 06/03 EDGE Box on Port ttyS22 (uCPE 7350) is pre-staged and ready to be shipped. 27/02 Order submitted via API; Pending SOF |  | Order submission | NEW uCPE 7350 and existing uCPE 7200 | TBC | Copper | Telstra Global and HGC Global Communications | 20-21/04/2023 | TBC |  | 160 Moo 17 Bangplee Ind. Estate Bangna-Trad Road KM 23 Tambol Bangsaothong, Samutprakarn, 10540, Thailand | 10540 | Thailand | Yutthana Nangla | +66 27051677 Ext. 1313 | Yutthana.Nangla@molnlycke.com | Level 1, factory building, server room
TH-BNK | 2217010 | Regional |  | SD-WAN | 40 Mbps-Khet Phra Khanong,TH | GTT/001804520 | GTT | On Track | 01/05 Still pending design amendment 24/04 Pending order amendment with new design solution. Reg the delivery: MHC: "AIS Support Tel: 084-360-8402 K’Goh(คุณโก๋). I have contacted to AIS that support on Summer Hub building for pre-information. - AIS will provide in house cabling to usage area, with standard ODF and switch. - TRUE can hire AIS fiber for MPLS monthly." 10/04 Escalated to VC. MHC to confim LCON is fully aware of this delivery. 03/04 Still pending more info 27/03 Additional cabling required (pending more details about the in-house cabling requirements) 20/03 Clarity over the solution design is still pending from SC, they advised that these might be put on hold 13/03 In progress; pending 'Provision Network - IP Port' and vendor FOC 20/02 YD: Missing TAD and LAN IP info Order confirmed |  | Site Survey | CON-C892FSP-KT-X1 and uCPE 7200 | uCPE Silverpeak WAN0: 49.229.48.100/29 uCPE MGMT VM IP: 49.229.48.99 Gateway: 49.229.48.97 LAN: 10.246.184.254/28 | Copper | SG.GS and CPA | TBC |  |  | 1778 Sukhumvit Rd, Summer Hub Offices, 2nd floor, Khet Phra Khanong, 10260, Thailand | 10260 | Thailand | Thanes Wanadonpisal | +668 3275 9409 | Thanes.Wanadonpisal@molnlycke.com | Level 4,comms, owned office
TH-CHO | 2227018 | Factory |  | NEW SD-WAN | 80 Mbps-Chonburi,TH | GTT/002602101 | Vendor | On Track | 01/05 Segment :: 12309168 :: GTT/002602101 is completed. Pending 2nd leg installation. 24/04 "Subnet: 10.245.97.240/28 10.245.97.254 GTT VRRP VIP 10.245.97.253 GTT Primary uCPE SD-WAN LAN0 10.245.97.252 GTT Secondary uCPE SD-WAN LAN0" 18/04 YD: IP details provided 10/04 Pending final solution and IPs "Do you have a /28 LAN subnet assigned for the new TH-CHO site? GTT will need it to proceed with the order and staging." 03/04 Add to DCF 27/03 Pending uCPE config and TAD update; PO Ticket: 7323662 (HPE-2TBHDD) 20/03 Pending design clarification 13/03 NetProv: Please add a link to the DCF (or attach it to the PON) 06/03 Vendor to contact LCON again to arrange an appointment LCON is not aware of this delivery (MHC to follow up) |  | Site Survey | uCPE 5300 and uCPE 9400 | TBC | Copper | HGC Global Communications x 2 | TBC |  |  | Mölnlycke Health Care (Thailand) Ltd. 700/461 Moo 7 Bangna-Trad Rd. Km.57 Amata Nakorn Industrial Estate (Bang Pakong) Tambol Donhuaroh, Amphur Muang, Chonburi, 20000, Thailand | 20000 | Thailand | Yutthana Nangla | +66 083-097-0203 | Yutthana.Nangla@molnlycke.com | 2nd floor, Amata Nakorn Industrial Estate (Bang Pakong), server room, factory building
US-AND | 2217024 | Factory |  | SD-WAN | 300 Mbps-Anderson,US | GTT/002592283 | GTT | Vendor Delivered | 01/05 Accedian NID installation rescheduled for 3rd May at 9 am EST. 24/04 Install date proposed by GTT 27th April at 9 am EST to finish the installation of Accedian MetroNID TE 1G plus SFP/fibre cables 18/04 TN: 1ZR4053Y0390598628 TTU Notes: - the new secondary uCPE 7350 was installed and booted up - HA link is connected and the LAN as well on the new device - AT&T and Spectrum have delivered on fiber handoff, there was no SFP shipped with the new uCPE and the old one (7200) does not have a SFP NIC, so likely a Accedian will have to be shipped to act as a MC for it 10/04 NEW uCPE install booked on 12th April at 9 am local time (call invitation sent to MHC). Pending installation. 03/04 Still pending installation date. Action plan to be confirmed. 27/03 Still pending MHC; New uCPE to be installed. 20/03 Activation date TBC 13/03 2 x fibre services delivered, pending GTT equipment installation. Date and time to be confirmed. 06/03 Pending Spectrum line delivery 27/02 uCPE delivered. Pending 2nd line installation. 20/02 uCPE 7350 shipped 1ZR4053Y0395840883 Pending new uCPE config. |  | uCPE install | uCPE 7350 + existing 7200 | TBC | SMF | AT&T Wholesale and Spectrum | TBC |  |  | 100 Schmid Plaza Rd, Anderson, SC, 29624-3830, USA | 29624-3830 | USA | Karen Thrasher | +1864-650-3281 | karen.thrasher@molnlycke.com | 1st floor, server room; warehouse building
US-BRU | 2234207 | Factory |  | SD-WAN | 500 Mbps-Brunswick,US | GTT/002609307 | Vendor | On Track | 01/05 Signed MOP sent to the vendor to proceed with delivery 24/04 uCPE 9400 - US-BRU Factory - no stock in Austin WH (case escalated). Pending 2 x fibre deliveries 10/04 Pending GTT uCPE config and shipment; vendor delivery is in progress 03/04 Vendor construction works 31/03 Pending uCPE config 27/03 Construction works required from the supplier (pending more information) 20/03 GTT to follow on 13/03 NO TAD 06/03 Pending install date 27/02 Pending vendor FOC 20/02 2 x orders submitted; TAD? 13/02 Pending ASR Pending validation |  | Fibre installation | NEW uCPE 9400 and existing uCPE 7200 | LAN subnet: 10.242.48.251/28 | Copper | FirstLight x 2 | TBC | TBC |  | 192 Admiral Fitch Ave Brunswick, ME 04011-2795 USA | 04011-2795 | USA | Ravish.Bhasin | +1678-492-8182 | ravish.bhasin@molnlycke.com | Level 2, factory building, server room
US-NOR | 2217091 | Regional |  | SD-WAN | 500 Mbps-Norcross,US | GTT/001972721 | GTT | On Track | 01/05 Still pending design amendment 24/04 Pending vendor FOC and PON amendment 10/04 Pending vendor FOC 03/04 CON-C892FSP-KT-X1 SN: FCZ2334C2G4 (delivered). Pending Vendor Construction. 31/03 TN 1ZR4053Y0391466750 for the Cisco CON-C892FSP-KT 20/03 Survey completed See below 06/03 Pending install date 27/02 Pending FOC 20/02 Comcast order submitted. Re-place current CPA with CPA-Enhanced; Missing floor number PW: Lvl 5 |  | Site Survey | uCPE 7200 and NEW CISCO C892FSP | uCPE Silverpeak WAN0: 12.197.187.99/28 uCPE MGMT VM IP: 12.197.187.98 Gateway: 12.197.187.97 LAN: 10.242.136.254/28 | Copper | Comcast and CPA | TBC | TBC |  | 5445 Triangle Pkwy, Norcross, GA 30092, USA | 30092 | USA | Kevin Rounds | +1 470-595-7466 | kevin.rounds@molnlycke.com | Floor is level 5, Rented office, Server Room
US-WIS | 2227245 | Factory |  | SD-WAN | 500 Mbps-Wiscasset,US | GTT/002602328 | GTT | Vendor Delivered | 01/05 ETD (estimated time of delivery) of GTT equipment is supposed to be today so we should see them next week. 24/04 Still pending uCPE 9400 config. 18/04 Media converter to be shipped + 2 x SFPs + 3 x 10m LC-LC SM fiber optic cable 10/04 Vendor lines delivered, pending GTT equipment 03/04 NEW uCPE 9400 to be shipped 31/03 Pending uCPE Config 20/03 Pending appointment 13/03 Provision completed with SPOF 06/03 Order is in progress; POP level diversity agreed between GTT and MHC See below 20/02 Pending CPE config. Handoff confirmation *Pending SPOF confirmation; Cancelation sunk cost is 119.75 in case one of the circuits gets cancelled by FirstLight. |  | Order submission | NEW uCPE 9400 and existing uCPE 7200 | TBC | SMF? Ok | FirstLight x 2 | TBC | TBC |  | 11 Twin Rivers Dr, Wiscasset, ME, 04578, USA | 4578 | USA | Ravish.Bhasin | +1678-492-8182 | ravish.bhasin@molnlycke.com | Level 1, factory building, server room
HK Gateway | 2222879 | Gateway |  | SD-WAN | 1000 Mbps-Tseung Kwan 0 Industrial Estate,HK | SD-WAN/01388180 | GTT | On Track | 01/05 We need to perform further clean-up according to the recent conversations with GTT NetProv engineer 24/04 Pending completion HKG GW was shut down and its resources were upgraded, then it was powered on and shapers + boost adjusted on the VM to 1Gbbps |  | Order validation | [7 empty] | 11 Chung Kwong Street Tseung Kwan 0 Industrial Estate MIssing Hong Kong |  | Hong Kong
HK Gateway | 2223107 | Gateway |  | SD-WAN | 1000 Mbps-Hong Kong,HK | SD-WAN/01388184 | GTT | On Track | 01/05 We need to perform further clean-up according to the recent conversations with GTT NetProv engineer 24/04 Pending completion Change completed in PON 2222879 |  | Order validation | [7 empty] | 11 Chung Kwong Street Tseung Kwan 0 Industrial Estate Hong Kong MISSING-ZIP Hong Kong
SG-SIN Gateway | 2223108 | Gateway |  | SD-WAN | 1000 Mbps-Singapore,SG | SD-WAN/01388193 | GTT | On Track | 01/05 We need to perform further clean-up according to the recent conversations with GTT NetProv engineer 24/04 Pending completion 21/03 SIN GW was shut down and its resources were upgraded, then it was powered on and shapers + boost adjusted on the VM to 1Gbbps 06/03 On track for 18th March, pending GTT recources 27/02 Pending out of hours support 20/02 MHC proposed date 18th March SAT, Downtime time from 15:00 to 23:00 CET the VDC VM will have to be stopped to increase CPU, RAM and Disk volume resources for it and then enabled, the customer to advise for a convenient time window to do so PW: Either do it on 19th february or 18th Mars |  | Order validation | [7 empty] | 110 Paya Lebar Rd Singapore 409009 Paya Lebar Rd Singapore 409009 Singapore | 409009 | Singapore | TBC | TBC | TBC | TBC
SG-SIN Gateway | 2223109 | Gateway |  | SD-WAN | 1000 Mbps-Singapore,SG | SD-WAN/01388200 | GTT | On Track | 01/05 We need to perform further clean-up according to the recent conversations with GTT NetProv engineer 24/04 Pending completion Target activation date 18th March |  | Order validation | [7 empty] | 110 Paya Lebar Rd Singapore 409009 Paya Lebar Rd Singapore 409009 Singapore | 409009 | Singapore | TBC | TBC | TBC | TBC
US-NYC Gateway | 2223110 | Gateway |  | SD-WAN | 1000 Mbps-New York,US | SD-WAN/01388116 | GTT | On Track | 01/05 We need to perform further clean-up according to the recent conversations with GTT NetProv engineer 24/04 Pending completion 21/03 NYC GW was shut down and its resources were upgraded, then it was powered on and shapers + boost adjusted on the VM to 1Gbbps Target activation date 18th March |  | Order validation | [7 empty] | 60 Hudson St Suite 901 New York, NY 10013 USA | 10013 | USA | TBC | TBC | TBC | TBC
US-NYC Gateway | 2223111 | Gateway |  | SD-WAN | 1000 Mbps-New York,US | SD-WAN/01388167 | GTT | On Track | 01/05 We need to perform further clean-up according to the recent conversations with GTT NetProv engineer 24/04 Pending completion Target activation date 18th March |  | Order validation | [7 empty] | 60 Hudson St Suite 901 New York, NY 10013 USA | 10013 | USA | TBC | TBC | TBC | TBC | t
US-LOS Gateway | 2223112 | Gateway |  | SD-WAN | 1000 Mbps-Los Angeles,US | SD-WAN/01388172 | GTT | On Track | 01/05 We need to perform further clean-up according to the recent conversations with GTT NetProv engineer 24/04 Pending completion 21/03 LAX GW was shut down and its resources were upgraded, then it was powered on and shapers + boost adjusted on the VM to 1Gbbps Target activation date 18th March |  | Order validation | [7 empty] | 707 Wilshire Blvd Los Angeles CA 90017 USA | 90017 | USA | TBC | TBC | TBC | TBC
US-LOS Gateway | 2223113 | Gateway |  | SD-WAN | 1000 Mbps-Los Angeles,US | SD-WAN/01388175 | GTT | On Track | 01/05 We need to perform further clean-up according to the recent conversations with GTT NetProv engineer 24/04 Pending completion Target activation date 18th March |  | Order validation | [7 empty] | 707 Wilshire Blvd Los Angeles CA 90017 USA | 90017 | USA | TBC | TBC | TBC | TBC
NL-KOO Gateway | 2223114 | Gateway |  | SD-WAN | 1000 Mbps-Schiphol-Rijk,NL | SD-WAN/01388525 | GTT | On Track | 01/05 We need to perform further clean-up according to the recent conversations with GTT NetProv engineer 24/04 AMS GW will require a MAC:Reterm) 21/03 AMS GW was shut down and its resources were upgraded, but it did not go up, likely due to a VDC resource issue ; a new AMS GW VM was deployed on our AMS24 NFV POD and the config was moved over to it ; Target activation date 18th March |  | Order validation | [7 empty] | Koolhovenlaan 120 Schiphol-Rijk Schiphol-Rijk 1119 NH Netherlands | 1119 NH | Netherlands | TBC | TBC | TBC | TBC
DE-ESC Gatway | 2223115 | Gateway |  | SD-WAN | 1000 Mbps-Eschborn,DE | SD-WAN/01388535 | GTT | On Track | 01/05 We need to perform further clean-up according to the recent conversations with GTT NetProv engineer 24/04 Pending completion 21/03 FRA GW was shut down and its resources were upgraded, then it was powered on and shapers + boost adjusted on the VM to 1Gbbps Target activation date 18th March |  | Order validation | [7 empty] | Schwalbacher Str. 60-62 Eschborn 65760 Germany | 65760 | Germany

## Risk Log
Risks Assessment Log
Customer |  |  | Mölnlycke Health Care | Project Start Date | 2023-01-03 |  | High Level Risks |  |  | 2
Customer Project Manager |  |  | Peter Wicander | Project End Date | TBC |  | Medium Level Risks |  |  | 10
GTT Project Manager |  |  | Yana Dzhineva | Project Code | PS-28956 |  | Low Level Risks |  |  | 5
Risk Analysis
Risk ID | Category |  | Risk Details | Risk Mitigation Plan |  | Company Owner | Risk Owner | Impact | Impact Level (Low 1- High 4) | Probability (Low 1- High 4) | Risk Score | Proximity | Risk Response | Date Raised | Risk Status/Notes | Level | Date Closed
PS-2503 - R001 | Planning |  | Incorrect addresses or post codes provided will lead to the Vendor order being rejected and will incur delays | The customer should check the addresses in the order form and the project master tracker to ensure the details are correct. |  | Client | Client HQ | Timeline | 4 | 1 | 4 | 1 - Likely this month |  |  |  | High
PS-2503 - R002 | Planning |  | Demarcation details and site contact information must be provided prior to Vendor orders being placed. If any changes are made to the site addresses during implementation. Changes to addresses may result in 3rd party providers cancelling orders. New orders will be placed and lead times will start again. | The customer must check the information provided and ensure that the correct details are submitted prior to the Vendors being ordered |  | Client | Client Local Representative | Timeline | 4 | 1 | 4 | 1 - Likely this month |  |  |  | High
PS-2503 - R003 | Design |  | The customer must provide any techincal information that has been requested by GTT within the agreed timeframe. Any delays will have an impact on the overall project plan | GTT will work closely with the Customer to ensure that delays in providing information are minimal. |  | GTT/ Client | Client Technical Team | Timeline | 4 | 3 | 12 | 1 - Likely this month |  |  |  | High
PS-2503 - R006 | Supplier Management |  | Delays and inconvenience will be caused if the 3rd party supplier turns up to site without prior arrangement made. | The Customer and GTT will work together to ensure site access is pre-arranged. Alternative dates will be arranged as quickly as possible if unauthorised visits take place. |  | GTT / Client | GTT Service Delivery Coordinator / Client Local Representative | Timeline | 4 | 2 | 8 | 2 - Likely next 2-3 months |  |  |  | High
PS-2503 - R007 | Communications |  | The Customer should assist with communications to their site contacts. Any failed visits will incur charges which will be passed on to the Customer. Delays will occur is the customer is unable to ensure third party site access within 24hrs notice. Access is required within this notice period during standard working hours. | GTT will arrange access with the site contact, the Customer is responsible to ensure the access is granted once the visit has been arranged. Additional charges will apply for failed site visits caused by the Customer. |  | Client | Client Local Representative | Timeline | 4 | 2 | 8 | 2 - Likely next 2-3 months |  |  |  | High
PS-2503 - R008 | Communications |  | If the Customer does not notify GTT of its LAN migration and testing schedule and as a result requires resource and support which may not be available without prior notice. | The Customer must notify GTT of LAN migration schedules and work closely with GTT to secure resource. |  | Client | Client Technical Team | Resources | 4 | 1 | 4 | 5 - Likely in over 12 months |  |  |  | Medium
PS-2503 - R009 | Implementation |  | Issues with the delivery of circuits from 3rd party providers such as circuit issues, site issues, exchange issues etc. | GTT will manage any delays internally and with 3rd party providers to resolve. An escalation matrix is in place if needed. |  | GTT | GTT Service Delivery | Timeline | 4 | 2 | 8 | 2 - Likely next 2-3 months |  |  |  | High
PS-2503 - R010 | Implementation |  | Vendor providers can only deliver to the entry point/meet me room of a building. In some cases Internal Cabling will be required | The Customer will be required to request and pay for any internal cabling that is required. |  | Client | Client Local Representative | Budget | 4 | 2 | 8 | 1 - Likely this month |  |  |  | High
PS-2503 - R011 | Implementation |  | If the hardware provided onsite is discovered to be faulty during installation and testing e.g. router, cables etc. | GTT will provide a replacement router as quickly as possible. GTT will then re-arrange an additional engineer visit. |  | GTT | GTT Service Delivery | Timeline | 4 | 1 | 4 | 5 - Likely in over 12 months |  |  |  | Medium
PS-2503 - R012 | Implementation |  | If there are Customer issues / conflicts during LAN migration. | GTT will assess any technical design / configuration issues with its technical design team at the time of the install. All Changes will be implemented as quickly as possible to resolve the issue. The Customer must accept the risk and note that incorrectly provided addressing schemas and ranges may affect delays. |  | GTT / Client | Client technical team | Timeline | 4 | 1 | 4 | 3 - Likely next 3-6 months |  |  |  | Medium
PS-2503 - R013 | Testing |  | Delays will happen when testing and migrating services and sites are impacted by resource availability from either party. | GTT has assigned a project team to provide support for the Customer to mitigate any internal resourcing issues. The Customer is responsible for ensuring adequate onsite and technical resource is available for installations and migrations. |  | GTT / Client | GTT Project Manager / Client Technical Team | Timeline | 4 | 3 | 12 | 1 - Likely this month |  |  |  | High
PS-2503 - R014 | Testing |  | If there is unexpected down time between the time of GTT WAN implementation and the Customer LAN migration due to a 3rd party supplier line fault. Faults can arise following WAN implementation when all testing may have been proved successful. | GTT has a fault logging procedure in which this issue will be logged and every effort made to resolve within Project timescales. The Customer must be aware of the risk and that tolerances may slip due to this. |  | GTT | GTT service delivery / GTT provisioning team | Timeline | 4 | 1 | 4 | 3 - Likely next 3-6 months |  |  |  | Medium
PS-2503 - R015 | Testing |  | If the fail-over between primary and back-up circuits fails in testing. | GTT will make every effort to review its router configuration and apply any changes as required during migration. However, the Customer must be aware of the risk and that tolerances may slip if the issue is not resolved. |  | GTT | GTT provisioning team | Solution | 4 | 1 | 4 | 3 - Likely next 3-6 months |  |  |  | Low
PS-2503 - R016 | Testing |  | If the guaranteed latency is not achieved during WAN testing. | GTT has a fault logging procedure in which this issue will be logged and every effort made to resolve within Project timescales. The Customer must be aware of the risk and that tolerances may slip due to this. |  | GTT | GTT service delivery / GTT provisioning team | Solution | 2 | 1 | 2 | 3 - Likely next 3-6 months |  |  |  | Medium
PS-2503 - R017 | Testing |  | If there are technical issues during WAN testing where a routing protocol is to be applied. | GTT will make every effort to review its router configuration and apply any Changes as required during migration to resolve and mitigate any slippage. However, the Customer must be aware of the risk and that tolerances may slip due to this. |  | GTT | GTT service delivery / GTT provisioning team | Solution | 4 | 1 | 4 | 4 - Likely next 3-6 months |  |  |  | High
PS-2503 - R018 | Supplier Management |  | Covid-19 pandemic can casue delay in vendor planned works. | GTT will make every effort to coordinate between vendor current delivery status and plan the installations with the Client |  | GTT / Client | GTT service delivery | Timeline | 4 | 4 | 16 | 2 - Likely next 2-3 months
© GTT Communications, Inc.

## Issue Log
Issue Log
Customer |  |  | Mölnlycke Health Care |  |  | Project Start Date |  | 2023-01-03 | Open Actions |  | 0
Customer Project Manager |  |  | Peter Wicander |  |  | Project End Date |  | TBC | On Hold Actions |  | 0
GTT Project Manager |  |  | Yana Dzhineva |  |  | Project Code |  | PS-28956 | Closed Actions |  | 0
Open Escalations
Issue Details |  |  |  | Issue Status | [6 empty] | Dates
Number | Category |  | Issue Assigned to | Descripton |  |  | Current Status |  |  | Status | Raised | Target | Updated | Complete
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
© GTT Communications, Inc. |  |  |  |  | Private and Confidential

## MoM Log (hidden)
Minutes Log
Customer |  |  | Lindorff |  | Project Start Date | 2022-12-20 | Current Minutes | 1
Customer Project Manager |  |  | Michał Mozdyniewicz |  | Project End Date |  | Past Minutes | 3
GTT Project Manager |  |  | Yana Dzhineva |  | Project Code | PS-2503
Number | Date Raised |  | Minute Description | [5 empty] | Status
1 | 29.7.2020 |  | 1. Budapest old – client to confirmed if all services are activated. According to GTT primary line is pending live activation. 2. Kleinmachnow and Eberswalde – waiting for LCON confirmation by local teams in Germany to be provided by client. 3. Ashtown – internal change request approved. Client to check with local team about date and time slot for vendor to install. 4. Rueil Malmaison - client to check if site is still under quarantine. 5. Goeteborg – still pending HO. GTT SD team is on it and working. 6. Stavanger – vendor will be on site to find exact demarcation where line was delivered. 7. Gent – date and time slot to be arranged. Dedicated engineer - Peter Damyanov to be involved in the activation call – because of specific configuration of the CPE needed. 8. Budapest new – client to check the status of the building and if server room and racks are ready. When CPE have to be shipped to check on which address to be sent – old or new one. 9. Frankfurt – both deliveries are put “on hold”. Next week all needed technical information will be available. 10. Bratislava – pending SOF to be signed. 11. Bari - pending SOF to be signed. 12. Athens – is on a quote level. 13. Tarnowskie Gory is on a quote level. | [5 empty] | Past Minute
2 | 5.8.2020 |  | 1. Milan – LCON and vendor agreed the installation will be in the first week of September. 2. Stockholm – client will check with LCON if the building is ready and GTT could proceed with line delivery. 3. Ashtown – pending LCON to confirm when he could arrange access. 4. Goeteborg – LA to be postponed till second half of August due to no available resources from Fujitsu. 5. Stavanger – client will check with landlord if there is in house cabling. GTT will check with vendor demarcation point. 6. Gent - no resources from client’ site till 17th of August. 7. Budapest old – client is trying to organize resources for LA to be performed. 8. Budapest new – pending information from client for the current status. 9. Frankfurt – client is working with SE to provide needed technical information. 10. Rueil Malmaison – client to send updated LCON. @Mirosveta Dudovska to check the current status. | [5 empty] | Past Minute
3 | 12.8.2020 |  | 1. Budapest old – pending Vidar (Fudjitsu) to start planning LA. 2. Stockholm - LCON is on vacation. @michal.mozdyniewicz@intrum.com to check if we could proceed with delivery of the line. @Mirosveta Dudovska to check if City Telecom is 3rd party provider of GTT/vendor. 3. Surray – start planning live activation. 4. Goetheborg primary line - @michal.mozdyniewicz@intrum.com to check if they could provide IPs to GTT SE in order CPE to be provisioned. 5. Budapest new - @Marcin.Pulkowski@intrum.com to check with LCON if the server room and rack are ready. 6. Stavanger – @Mirosveta Dudovskato check with vendor about in house cabling. 7. Frankfurt Azure - @michal.mozdyniewicz@intrum.com to check with GTT SE about required technical information to be filled in and start working on delivery. | [5 empty] | Past Minute
4 | 19.8.2020 |  | 1. Stockholm – LCON confirmed both vendors contacted him yesterday. @Mirosveta Dudovska to check with vendor if there are any additional requirements about in house cabling with vendor. 2. Goteborg - @Mirosveta Dudovska to check with vendor what is the current status with the in house cabling. 3. Stavanger – pending vendor to advise about in house cabling. 4. Valladolid - @Mirosveta Dudovska to check with SD about the current status. 5. Budapest old – pending client about live activation. 6. Eberswalde - @Mirosveta Dudovska to check with SD about possible EDD. 7. Ashtown – issues with building management about providing access. It will be postponed until September. 8. Hamburg – line to be live activated during the failover test with GTT Support team. 9. Budapest new – two Disco PONs to be added in the tracker. @Michał Mozdyniewicz to confirm the current ones. 10. Bari – pending confirmation by GTT. 11. Athens – pending PO by GTT. 12. New column with vendors to be added to in the Master tracker. | [5 empty] | Current
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
© GTT Communications, Inc. |  |  |  | Private and Confidential

## Actions Log (hidden)
Actions Log
Customer |  |  | Mitsubishi Chemical UK Limited |  |  | Project Start Date |  | 2023-01-03 | Open Actions |  | 0
Customer Project Manager |  |  | Peter Wicander |  |  | Project End Date |  | 2023-11-01 | On Hold Actions |  | 0
GTT Project Manager |  |  | Yana Dzhineva |  |  | Project Code |  | PS-6806 | Closed Actions |  | 0
Action Details |  |  |  | Action Status | [6 empty] | Dates
Number | Category |  | Action Assigned to | Descripton |  |  | Current Status |  |  | Status | Raised | Target | Updated | Complete
1 | Planning
2 | Planning
3 | Planning
4 | Planning
5 | Planning
6 | Supplier Management
7 | Communications
8 | Communications
9 | Communications
10 | Communications
11
12
13
14
15
16
17
18
19
20
© GTT Communications, Inc. |  |  |  |  | Private and Confidential

## Cost Register
Cost Register
Customer |  |  | Mölnlycke Health Care |  |  | Project Start Date | 2023-01-03 |  | Total Costs |  | 0
Customer Project Manager |  |  | Peter Wicander |  |  | Project End Date | 2023-11-01
GTT Project Manager |  |  | Yana Dzhineva |  |  | Project Code | PS-28956
Description |  |  |  | Cost Details | [5 empty] | Acceptance
Number | Cost Description |  |  | Date Raised |  | Site Name | Cost | To Be Charged To |  | Accepted By |  | Date | Billing
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
© GTT Communications, Inc. |  |  |  |  | Private and Confidential

## Communications Plan
Communications Plan
Customer |  |  | Mölnlycke Health Care |  |  |  | Project Start Date |  | 2023-01-03
Customer Project Manager |  |  | Peter Wicander |  |  |  | Project End Date |  | TBC
GTT Project Manager |  |  | Yana Dzhineva |  |  |  | Project Code |  | PS-28956
GTT Project Team
Name | Jan Engels |  |  | Position | Director, Project Management |  |  | Company | GTT
Mobile |  |  |  | Phone | +32 25885330 |  |  | Email | jan.engels@gtt.net
| Nic Douglas |  |  |  | Senior Manager, North Europe |  |  |  | nic.douglas@gtt.net
Name | Yana Dzhineva |  |  | Position | Project Manager |  |  | Company | GTT
Mobile |  |  |  | Phone | + 44 2038738686 |  |  | Email | yana.dzhineva@gtt.net
Name | Ricardo Sierra Tanvi Sehgal |  |  | Position | Solution Consultant |  |  | Company | GTT
Mobile |  |  |  | Phone | +34 674 112 976 |  |  | Email | ricardo.sierra@gtt.net
Name | Boelie Vigeveno |  |  | Position | Account Manager |  |  | Company | GTT
Mobile |  |  |  | Phone | +31629094884 |  |  | Email | boelie.vigeveno@gtt.net
Customer Project Team
Name | Peter Wicander |  |  | Position | Service Area Owner Enterprise Infrastructure Global IT - Infrastructure and Operations |  |  | Company | Mölnlycke Health Care
Mobile | +46 31 352 37 25 |  |  | Phone | +46 737 – 73 37 25 (mobile extension) |  |  | Email | peter.wicander@molnlycke.com
Name |  |  |  | Position |  |  |  | Company
Mobile |  |  |  | Phone |  |  |  | Email
Project Team Meeting
Frequency | weekly |  |  | Day & Time | Monday at 2 :00 PM CET |  |  | Location | Teams
Project Board Meeting
Frequency | monthly |  |  | Day & Time | Wednesday |  |  | Location | Teams
Any Bespoke Customer Requirements
© GTT Communications, Inc. | [5 empty] | Private and Confidential